## Defect Log
Defect_ID | Title | Description | Module | Severity | Priority | Status | Found_In_Test_Case | Reported_By | Assigned_To
DEF_001 | EMI Calculation mismatch for 12-month tenure | The EMI calculated by the system for a $10,000 loan at 12% for 12 months shows $890.00 instead of $888.49. | Interest Engine | High | High | Open | TC_11 | QA_Lead | Dev_Team_A
DEF_002 | SSN Masking not applied in UI | The SSN field displays full digits on the Application Review screen. It should be masked (e.g., ***-**-1234). | Security/PII | Critical | High | In Progress | TC_17 | Security_Tester | Frontend_Dev
DEF_003 | Unauthorized user can trigger loan approval API | A user with 'Customer' role is able to call /api/v1/applications/{id}/approve and receive a 200 OK. | API / Security | Critical | Urgent | Open | TC_14/TC_20 | QA_API_Tester | Backend_Dev
DEF_004 | Audit log missing for 'Rejected' status change | When a loan is rejected, no entry is created in the Audit_Logs table. Logs for 'Approved' work correctly. | Database / Audit | Medium | Medium | Fixed | TC_18 | DB_Tester | DB_Admin
DEF_005 | Application allows 17-year-old applicants | System accepts DOB that results in an age of 17 years and 11 months. Should be restricted to 18+. | Loan Application | High | Medium | New | TC_23 | QA_Tester_1 | Dev_Team_B
DEF_006 | Credit check API returns 500 on timeout | When the third-party credit bureau times out, the system returns a 500 Internal Server Error instead of a graceful retry/error. | Integrations | Medium | Low | Open | TC_21 | QA_API_Tester | Backend_Dev